## Capacity
รายชื่อสมาชิก | รหัสนักศึกษา | จำนวนชม.ที่สามารถทำงานได้ใน Sprint
นางสาวชญาณิศ ธานี | 633021124-4 | 12
นายธราดล วิชัย | 653380019-1 | 12
นายวสิษฐ์พล พันชนกกุล | 653380023-0 | 11
นางสาวสิริวมล แก้วคุ้ม | 653380155-3 | 12
นายธีระภัทร สีทา | 653380269-8 | 16
นางสาวพัทธ์ธีรา ธีระรุจินนท์ | 653380275-3 | 13
นายพิชญ์พงศ์ สนทอง | 653380276-1 | 11
นายสุรภูมิ มณีราชกิจ | 653380283-4 | 10
จำนวนชั่วโมงรวม = |  | 97

## Task Estimation
Story ID | Task ID | Task name | Description | Estimate Effort (hrs.) | Committed at Sprint no. | Actual Time (hrs.)
S2 | 1 | User page - Import Page | User page - Import Page | 1 | 2 | 1
S2 | 2 | User page - Create Page | User page - Create Page | 1 | 2 | 1
S2 | 3 | Permission page - Create Page | Permission page - Create Page | 1 | 2 | 1
S2 | 4 | Manage Patent - Create Page | Manage Patent - Create Page | 1 | 2 | 1
S2 | 5 | Manage Fund - Create Page | Manage Fund - Create Page | 1 | 2 | 1
S2 | 6 | Roles page - Create Page | Roles page - Create Page | 1 | 2 | 1
S2 | 7 | Manage Paper(Published research) - Create Page | Manage Paper(Published research) - Create Page | 1 | 2 | 1
S2 | 8 | Manage Research Project- Create Page | Manage Research Project- Create Page | 1 | 2 | 1
S2 | 9 | Manage Expertise page - Create Page | Manage Expertise page - Create Page | 1 | 2 | 1
S2 | 10 | Manage Program page - Create Page | Manage Program page - Create Page | 1 | 2 | 1
S2 | 11 | Manage Program page - Update Page | Manage Program page - Update Page | 1 | 2 | 1
S2 | 12 | Department page - Create Page | Department page - Create Page | 1 | 2 | 1
S2 | 13 | Manage Book page - Create Page | Manage Book page - Create Page | 1 | 2 | 1
S2 | 14 | Manage Research Group - Create Page | Manage Research Group - Create Page | 1 | 2 | 1
S2 | 15 | User page - Create + import Page | User page - Create + import Page | 1 | 2 | 1
S2 | 16 | Researchers Page | Researchers Page | 1 | 2 | 1
S2 | 17 | ResearchGroup Page | ResearchGroup Page | 1 | 2 | 1
S2 | 18 | Home page | Home page | 1 | 2 | 1
S2 | 19 | Research Project Page | Research Project Page | 1 | 2 | 1
S2 | 20 | ResearchGroup Detail Page | ResearchGroup Detail Page | 1 | 2 | 1
S2 | 21 | Research_Detail Page | Research_Detail Page | 1 | 2 | 1
S2 | 22 | Manage Fund - Update Page | Manage Fund - Update Page | 1 | 2 | 1
S2 | 23 | Manage Research Project - Update Page | Manage Research Project - Update Page | 1 | 2 | 1
S2 | 24 | Manage Research Group - Update Page | Manage Research Group - Update Page | 1 | 2 | 1
S2 | 25 | Manage Paper(Published research) - Update Page | Manage Paper(Published research) - Update Page | 1 | 2 | 1
S2 | 26 | User page - Update Page | User page - Update Page | 1 | 2 | 1
S2 | 27 | Manage Expertise page - Update Page | Manage Expertise page - Update Page | 1 | 2 | 1
S2 | 28 | Department page - Update Page | Department page - Update Page | 1 | 2 | 1
S2 | 29 | เพิ่มปุ่มเปลี่ยนภาษา | เพิ่มปุ่มเปลี่ยนภาษา | 1 | 2 | 1
S2 | 30 | Profile Page | Profile Page | 1 | 2 | 1
S2 | 31 | Report Page front | Report Page front | 1 | 2 | 1
S2 | 32 | Dashboard Page | Dashboard Page | 1 | 2 | 1
S2 | 33 | Login Page | Login Page | 1 | 2 | 1
S2 | 34 | Manage Fund Page | Manage Fund Page | 1 | 2 | 1
S2 | 35 | Roles page | Roles page | 1 | 2 | 1
S2 | 36 | Manage Research Project Page | Manage Research Project Page | 1 | 2 | 1
S2 | 37 | Manage Patent Page | Manage Patent Page | 1 | 2 | 1
S2 | 38 | User page | User page | 1 | 2 | 1
S2 | 39 | Manage Research Group Page | Manage Research Group Page | 1 | 2 | 1
S2 | 40 | Permission page | Permission page | 1 | 2 | 1
S2 | 41 | Manage Paper Page (Published research) | Manage Paper Page (Published research) | 1 | 2 | 1
S2 | 42 | Manage Book page | Manage Book page | 1 | 2 | 1
S2 | 43 | Manage Program page | Manage Program page | 1 | 2 | 1
S2 | 44 | User page | User page | 1 | 2 | 1
S2 | 45 | Department page | Department page | 1 | 2 | 1
S2 | 46 | Manage Expertise page | Manage Expertise page | 1 | 2 | 1
S2 | 47 | User page - view Page | User page - view Page | 1 | 2 | 1
S2 | 48 | Manage Paper (Published research) - view Page | Manage Paper (Published research) - view Page | 1 | 2 | 1
S2 | 49 | Roles page - view Page | Roles page - view Page | 1 | 2 | 1
S2 | 50 | Manage Expertise page - view Page | Manage Expertise page - view Page | 1 | 2 | 1
S2 | 51 | Manage Research Project - view Page | Manage Research Project - view Page | 1 | 2 | 1
S2 | 52 | Manage Patent - view Page | Manage Patent - view Page | 1 | 2 | 1
S2 | 53 | Manage Program page - view Page | Manage Program page - view Page | 1 | 2 | 1
S2 | 54 | Manage Research Group - view Page | Manage Research Group - view Page | 1 | 2 | 1
S2 | 55 | Manage Book page - view Page | Manage Book page - view Page | 1 | 2 | 1
S2 | 56 | User page - view Page | User page - view Page | 1 | 2 | 1
S2 | 57 | Permission page - view Page | Permission page - view Page | 1 | 2 | 1
S2 | 58 | Department page - view Page | Department page - view Page | 1 | 2 | 1
S2 | 59 | Manage Fund - view Page | Manage Fund - view Page | 1 | 2 | 1
S2 | 60 | Manage Paper(Published research) - delete Page | Manage Paper(Published research) - delete Page | 1 | 2 | 1
S2 | 61 | Manage Research Group - delete Page | Manage Research Group - delete Page | 1 | 2 | 1
S2 | 62 | Manage Research Project- delete Page | Manage Research Project- delete Page | 1 | 2 | 1
S2 | 63 | Manage Book page - delete Page | Manage Book page - delete Page | 1 | 2 | 1
S2 | 64 | Manage Patent - delete Page | Manage Patent - delete Page | 1 | 2 | 1
S2 | 65 | Manage Fund - delete Page | Manage Fund - delete Page | 1 | 2 | 1
S2 | 66 | Roles page - delete Page | Roles page - delete Page | 1 | 2 | 1
S2 | 67 | User page - delete Page | User page - delete Page | 1 | 2 | 1
S2 | 68 | Manage Program page - delete Page | Manage Program page - delete Page | 1 | 2 | 1
S2 | 69 | Department page - delete Page | Department page - delete Page | 1 | 2 | 1
S2 | 70 | Permission page - delete Page | Permission page - delete Page | 1 | 2 | 1
S2 | 71 | Manage Expertise page - delete Page | Manage Expertise page - delete Page | 1 | 2 | 1
S2 | 72 | Manage Patent - Update Page | Manage Patent - Update Page | 1 | 2 | 1
S2 | 73 | Roles page - Update Page | Roles page - Update Page | 1 | 2 | 1
S2 | 74 | Manage Book page - Update Page | Manage Book page - Update Page | 1 | 2 | 1
S2 | 75 | Permission page - Update Page | Permission page - Update Page | 1 | 2 | 1
S2 | 76 | API Status Page | API Status Page | 1 | 2 | 1
S2 | 77 | navbar menu This is Student | navbar menu This is Student | 1 | 2 | 1
S2 | 78 | navbar menu Manage Publications | navbar menu Manage Publications | 0 | 2 | 0
S2 | 79 | navbar menu manage apply research assistant | navbar menu manage apply research assistant | 1 | 2 | 1
S2 | 80 | test Home page | test Home page | 1 | 2 | 1
S2 | 81 | test Researchers Page | test Researchers Page | 1 | 2 | 1
S2 | 82 | test Research_Detail Page | test Research_Detail Page | 1 | 2 | 1
S2 | 83 | test Login page | test Login page | 1 | 2 | 1
S2 | 84 | test API Status Page | test API Status Page | 1 | 2 | 1
S2 | 85 | test navbar menu This is Student | test navbar menu This is Student | 1 | 2 | 1
S2 | 86 | test navbar menu Manage Publications | test navbar menu Manage Publications | 1 | 2 | 1
S2 | 87 | test show user profile -> account | test show user profile -> account | 1 | 2 | 1
S2 | 88 | test navbar menu manage apply research assistant | test navbar menu manage apply research assistant | 1 | 2 | 1
S2 | 89 | test navbar menu Manage hightlight | test navbar menu Manage hightlight | 1 | 2 | 1
|  |  | Total Efforts (hrs.) : | 88